13. System Development Methodology

1.Overview

This section explains the methodology Vertex IT Solution will take to developing the BINCOL Online Commercial Waste Collection System (CWCS); these include the methodologies that have been considered, methodology selection, and the methodology consideration in relation to the 5-member development team and the 12-week timeline outlined.

2. Comparison and Selection of Methodology

Four methodologies were evaluated in regard to the characteristics of this project: 49 functional requirements and 15 non-functional ones, fixed twelve weeks deadline, requirement likely to change (Risk R1), dependence on third party map, payment and email services and small multi-role team.

| Methodology | Strengths | Weaknesses for the CWCS Project | Outcome |
| --- | --- | --- | --- |
| Waterfall | Structured and easily documented with well-defined sign-off for each phase. | Analysis comes after requirements freeze, in contravention of Risk R1. Nearly all such working software is not adopted until towards the end, and map and payment glitches would come out too late to fix. | Rejected |
| V-Model | Relates a test stage to each development stage providing excellent verification. | Saves the same Waterfall rigidity; if there is a late change, specification and matching test level must be changed. | Rejected |
| Spiral | Payment and personal information system suiting - risk driven. | Each cycle needed twelve weeks as this was too much work for a five-member team to prototype and risk analyse. | Rejected |
| Agile - Scrum | Increments created in time-boxed sprints; embracing controlled change; ceremonies lightweight for small team. | Needs disciplined backlog management, and tends to generate less formal documentation; must make a conscious effort to deliberate documentation. | Selected |

3. Justification for Agile Scrum

- Absorbs change. Risk R1 makes frequent alterations to their requirements, and Scrum alters the backlog at the sprint boundary where change does not render work invalid.

- Protects the deadline. Since it's time-boxed and the backlog prioritised, the lowest value items, such as FR36, AI Route Suggestion, are pushed back, effectively to the next release, given that the scope statement already has that as optional for the first release.

- Exposes risk early. Map, payment and email integration are all implemented within sprints, meaning that any failure that is encountered as part of integration is readily apparent, and at that point an alternative could be introduced.

- Embeds security and documentation. The sprint items are not documented in a pre-release type audit, but rather as security acceptance criteria, and the less documentation in Scrum is compensated for by the fact that the SRS is controlled baseline.

Figure 13.1: The Scrum cycle adopted for the CWCS project

4 .Scrum Roles Mapped to the Project Team

| Team Member | Scrum Role | Responsibilities Within the Methodology |
| --- | --- | --- |
| Md Imran Hossain | Scrum Master (Project Manager) | Facilitates events, keeps sprint board updated, gets rid of impediments and keeps the sprint protected from scope change. |
| Fahad Al Jobayer | Technical Lead | Technical design ownership, checks for conformity with MVC (NFR11), maintains the repository, codes before acceptance. |
| Debisha Thapa | Development Team | Implements database increment and keeps integrity (NFR5) and provides security controls (NFR6-NFR8) and checks backup restoration. |
| Sharmen Akter Urme | Development Team | Solves problems, documents the results of ceremonies and files project documentation. |
| Fiza Taskeya | Product Owner (proxy) | Owns and prioritises the backlog, drafts user stories including acceptance criteria and accepts each increment to the system with regard to its user story. |

Since BINCOL is not able to provide a daily representative, the Business Analyst performs the role of Proxy Product Owner. Priority decisions are validated with the client during the sprint review and if the client changes their mind, a change request is logged.

5 .Scrum Events and Artefacts

The goal and backlog items that will be worked on during the sprint are agreed by performing sprint planning (90 minutes) at the start of each sprint. The stand-ups are 15 minutes, but only occur three times a week because the team is not co-located and the situation is asynchronous—between the stand-ups they leave updates for the team on the team channel. Refine backlog is done during the middle of a sprint. At the end of each sprint a sprint review is held with the client, where the increment is shown to the client and feedback requested, and a retrospective held where one process improvement is agreed.

Four artefacts are maintained including the product backlog (set of user stories with associated FR or NFR identified as issues in the shared GitHub repository and prioritised); increased, sprint backlog and sprint board and burndown chart to identify slippage in time to take action within the sprint.

6. Sprint Plan

Twelve-week plan: 6 sprints, each consisting of 2 weeks of work. Most later requirements depend on most of the foundational capabilities that are delivered first and security and recovery is done at a set point.

| Sprint | Weeks | Requirements | Key Outcomes |
| --- | --- | --- | --- |
| 0 Inception | 1–2 | Planning deliverables | Requirements catalogue, WBS and Gantt chart, risk register and interim SRS report; XAMPP or Laragon environment has been set up and repository and backlog have been created. |
| 1 Foundation and Security | 3–4 | FR01–FR08; NFR6–NFR8, NFR11, NFR12 | This is sprint one of the MVC skeleton, which includes registration, email verification and login/role based access for customer, staff, driver and admin user types; account management; bcrypt hashing and site-wide HTTPS. |
| 2 Service Configuration | 5–6 | FR09–FR17; NFR9, NFR10 | Storage locations and selection of branches and providers to upload documents; classification of waste and type of bin; add validation to prevent hazardous waste from being added to regular bins; responsive WCAG 2.1 AA Base templates. |
| 3 Booking and Scheduling | 7–8 | FR18–FR26; NFR1, NFR5 | One-time & recurring pickups, estimated cost prior to booking, staff approval, rescheduling, status tracking, conflict avoidance; tests performed on page loading within the 3 second mark. |
| 4 Dispatch and Mapping | 9–10 | FR27–FR36; NFR2, NFR3 | Truck and driver records, assignment and capacity validation, driver daily schedule and status update, map view and optimized routes, 100 user load testing. Week 10: Reviewing code with other people (from a developer who does not write the module) based on OWASP Top 10. |
| 5 Billing and Release | 11–12 | FR37–FR49; NFR4, NFR13–NFR15 | Invoicing, online payment, transaction log and reminders; notifications and messaging; reporting, export and analytics; service rating. Week 11: backups restored onto a test server and checking the 30-minute recovery goal. Week 12: user acceptance testing, deployment, training and handing over. |

7. Definition of Done

An item is complete only when it does meet Acceptance Criteria – meets the MVC (NFR11) – commented (NFR12) – validates input to protect against SQL injection, cross-site scripting, and cross-site request forgery (NFR7) – scope all queries to the authenticated user (a customer can only see his/her own branches, jobs and invoices) – it is reviewed by a member other than its own author – it is unit and integration tested – is rendered properly on mobile and desktop (NFR9) – it is deployed to a test environment and documentation is updated.

8 .Standards, Traceability and Change Control

Development is built with MVC and deployed locally via XAMPP or Laragon, with three environments (dev, shared test and prod) each in a different region in Australia because of the NFR15 requirement for data residency. Only branches the work per backlog item and merges it after peer review – no credentials in the repository and no card details stored by the application.

All the backlog items are linked to their FR or NFRs, and this can be traced to the sprint where it was delivered and then to the test case in Section 14 to verify that it has been met. Change requests are evaluated for impact and added to a future sprint only and never to an ongoing sprint – if there will be a higher work volume, an item of equal or lower priority will be removed, so that the SPL will not be exceeded.

9. Risk Control and Link to Testing

Risk categories that are addressed and controlled by the methodology include the requirement drift risk in sprint reviews (R1), the cyberattack risk in embedded security work (R2), the recovery risk in Week 10 review (R3), the exposure to defects on Week 10 recovery found during tests performed in the sprint (R4), the visibility of data loss in the shared repository (R5), and the spread of knowledge of the modules in peer review, reducing vulnerability to unavailability (R6). As described in Section 14 unit and integration testing is done on an ongoing basis throughout the sprints, system testing is done at the end of each sprint and user acceptance testing is done during Week 12, but for each sprint a shippable increment is produced.

References

- Schwaber, K. and Sutherland, J. (2020) The Scrum Guide: The Definitive Guide to Scrum: The Rules of the Game. Available at: https://scrumguides.org/scrum-guide.html (Accessed: 11 August 2026).

- Beck, K. et al. (2001) Manifesto for Agile Software Development. Available at: https://agilemanifesto.org/ (Accessed: 11 August 2026).

- OWASP Foundation (2021) OWASP Top 10:2021. Available at: https://owasp.org/Top10/2021/ (Accessed: 11 August 2026).

- World Wide Web Consortium (W3C) (2025) Web Content Accessibility Guidelines (WCAG) 2.1. Available at: https://www.w3.org/TR/WCAG21/ (Accessed: 11 August 2026).

- GitHub (2026) About Git. GitHub Docs. Available at: https://docs.github.com/en/get-started/using-git/about-git (Accessed: 11 August 2026).

- PHP Documentation Group (2026) password_hash — Creates a password hash. PHP Manual. Available at: https://www.php.net/manual/en/function.password-hash.php (Accessed: 11 August 2026).